## PV (hidden)
Count of asofdate | Column Labels
Row Labels | 2019-02-28 | 2019-03-31 | Grand Total
ABC System | 7 | 6 | 13
BCD System | 77 | 80 | 157
CDE System | 13 | 12 | 25
DEF System | 5 | 5 | 10
EFG System | 2 | 2 | 4
FGH System | 8 | 7 | 15
Grand Total | 112 | 112 | 224

## GRM_Issue_Repository
Management_Owner | Issue_Owner | Source_of_Issue | Source_System | Issue_ID | Issue_Subject | OECD | RECD | Level | Notes(Status Update) | CCAR_v.non-CCAR | Completion Date | MM | YYYY | asofdate
Owner1 | Owner2 | SEL | ABC System | 93 | Data definitions | 2020-12-31 | 2019-06-28 | Type 3 - Moderate | In progress | CCAR | 2019-06-28 | JUN | 2019 | 2019-02-28
Owner1 | Owner4 | GEL | ABC System | ISSUE-00001116 | Data definitions | 2020-12-31 | 2019-03-31 | Type 3 - Moderate | In progress | CCAR | 2019-03-31 | MAR | 2019 | 2019-02-28
Owner1 | Owner4 | GEL | ABC System | ISSUE-00001117 | Data definitions | 2019-03-31 | 2019-05-01 | Type 2 - High | In progress | CCAR | 2019-05-01 | MAY | 2019 | 2019-02-28
Owner1 | Owner4 | SEL | ABC System | ISSUE-00001118 | Data definitions | 2019-12-31 | 2025-12-31 | Type 2 - High | In progress | Non-CCAR | 2025-12-31 | DEC | 2025 | 2019-02-28
Owner1 | Owner4 | SEL | ABC System | ISSUE-00001119 | Data definitions | 2019-06-30 | 2020-12-31 | Type 2 - High | In progress | CCAR | 2020-12-31 | DEC | 2020 | 2019-02-28
Owner1 | Owner4 | SEL | ABC System | 1040 | Data definitions | 2019-11-01 | 2019-12-31 | Type 1 - Critical | In progress | CCAR | 2019-12-31 | DEC | 2019 | 2019-02-28
Owner1 | Owner1 | SEL | ABC System | 1075 | Data definitions | 2019-10-30 | 2019-03-31 | Type 3 - Moderate | In progress | Non-CCAR | 2019-03-31 | MAR | 2019 | 2019-02-28
Owner1 | Owner1 | SEL | BCD System | 1162 | Data definitions | 2019-04-05 | 2019-03-31 | Type 2 - High | In progress | Non-CCAR | 2019-03-31 | MAR | 2019 | 2019-02-28
Owner1 | Owner1 | SEL | DEF System | 1253 | Data definitions | 2020-12-31 |  | Type 2 - High | In progress | Non-CCAR | 2020-12-31 | DEC | 2020 | 2019-02-28
Owner1 | Owner2 | SEL | DEF System | 1301 | Data definitions | 2019-12-31 |  |  | In progress | Non-CCAR | 2019-12-31 | DEC | 2019 | 2019-02-28
Owner1 | Owner3 | SEL | DEF System | 1077 | Data definitions | 2018-01-08 |  |  | In progress | Non-CCAR | 2018-01-08 | JAN | 2018 | 2019-02-28
Owner1 | Owner3 | SEL | DEF System | 1302 | Data definitions | 2018-01-31 |  |  | In progress | Non-CCAR | 2018-01-31 | JAN | 2018 | 2019-02-28
Owner1 | Owner3 | SEL | DEF System | 1260 | Data definitions | 2019-10-30 |  |  | In progress | Non-CCAR | 2019-10-30 | OCT | 2019 | 2019-02-28
Owner1 | Owner3 | SEL | CDE System | 1281 | Data definitions | 2019-10-30 |  |  | In progress | Non-CCAR | 2019-10-30 | OCT | 2019 | 2019-02-28
Owner1 | Owner2 | SEL | CDE System | IS003447 | Data definitions | 2018-12-03 |  |  | In progress | Non-CCAR | 2018-12-03 | DEC | 2018 | 2019-02-28
Owner1 | Owner4 | GEL | CDE System | IS003448 | Data definitions | 2018-12-03 |  |  | In progress | Non-CCAR | 2018-12-03 | DEC | 2018 | 2019-02-28
Owner1 | Owner4 | GEL | CDE System | IS003449 | Data definitions | 2019-09-30 |  | Type 3 - Moderate | In progress | N/A | 2019-09-30 | SEP | 2019 | 2019-02-28
Owner1 | Owner4 | GEL | CDE System | IS003450 | Data definitions | 2019-08-31 |  | Type 3 - Moderate | Open Issue Need to Close Out | N/A | 2019-08-31 | AUG | 2019 | 2019-02-28
Owner1 | Owner3 | LEN | CDE System | IS003451 | Data definitions | 2019-08-31 |  | Type 3 - Moderate | In progress | N/A | 2019-08-31 | AUG | 2019 | 2019-02-28
Owner1 | Owner3 | LEN | CDE System | IS003452 | Data definitions | 2020-02-28 |  | Type 2 - High | In progress | N/A | 2020-02-28 | FEB | 2020 | 2019-02-28
Owner1 | Owner3 | LEN | CDE System | FND-139 | Data definitions | 2019-08-31 |  | Type 2 - High | In progress | N/A | 2019-08-31 | AUG | 2019 | 2019-02-28
Owner1 | Owner3 | LEN | CDE System | FND-140 | Data definitions | 2019-09-30 |  | Type 2 - High | In progress | N/A | 2019-09-30 | SEP | 2019 | 2019-02-28
Owner1 | Owner2 | RDC | CDE System | FND-141 | Data definitions | 2020-03-31 |  | Type 2 - High | In progress | N/A | 2020-03-31 | MAR | 2020 | 2019-02-28
Owner1 | Owner4 | RDC | CDE System | FND-142 | Data definitions | 2020-03-31 |  |  | Open Issue Need to Close Out | N/A | 2020-03-31 | MAR | 2020 | 2019-02-28
Owner1 | Owner1 | FFF | CDE System | FND-143 | Data definitions | 2020-03-31 |  |  | Open Issue Need to Close Out | N/A | 2020-03-31 | MAR | 2020 | 2019-02-28
Owner1 | Owner2 | EEE | CDE System | FND-144 | Data definitions | 2019-08-31 |  |  | Open Issue Need to Close Out | N/A | 2019-08-31 | AUG | 2019 | 2019-02-28
Owner1 | Owner3 | EEE | BCD System | FND-145 | Data definitions | 2019-09-30 |  | Type 2 - High | Open Issue Need to Close Out | N/A | 2019-09-30 | SEP | 2019 | 2019-02-28
Owner2 | Owner4 | GGG | BCD System | FND-146 | Data definitions | 2018-12-31 |  | Type 2 - High | Open Issue Need to Close Out | N/A | 2018-12-31 | DEC | 2018 | 2019-02-28
Owner2 | Owner5 | EEE | BCD System | FND-147 | Data definitions | 2019-10-30 | 2019-08-15 | Type 2 - High | Open Issue Need to Close Out | N/A | 2019-08-15 | AUG | 2019 | 2019-02-28
Owner2 | Owner5 | SEL | BCD System | FND-148 | Data definitions | 2019-06-01 | 2019-08-15 | Type 3 - Moderate | Open Issue Need to Close Out | N/A | 2019-08-15 | AUG | 2019 | 2019-02-28
Owner2 | Owner5 | SEL | BCD System | FND-149 | Data definitions | 2019-09-30 | 2019-08-15 |  | Open Issue Need to Close Out | N/A | 2019-08-15 | AUG | 2019 | 2019-02-28
Owner2 | Owner4 | SEL | BCD System | IS004958 | Data definitions | 2018-10-30 | 2020-03-30 |  | Open Issue Need to Close Out | N/A | 2020-03-30 | MAR | 2020 | 2019-02-28
Owner2 | Owner4 | SEL | BCD System | IS004959 | Data definitions | 2019-01-31 | 2018-09-28 |  | In progress | N/A | 2018-09-28 | SEP | 2018 | 2019-02-28
Owner2 | Owner4 | SEL | BCD System | IS004960 | Data definitions | 2019-11-01 | 2018-09-28 |  | In progress | N/A | 2018-09-28 | SEP | 2018 | 2019-02-28
Owner2 | Owner3 | SEL | BCD System | IS004961 | Data definitions | 2019-10-30 | 2019-03-31 |  | Open Issue Need to Close Out | N/A | 2019-03-31 | MAR | 2019 | 2019-02-28
Owner2 | Owner5 | GGG | BCD System | IS004962 | Data definitions | 2019-04-05 |  | Type 1 - Critical | In progress | N/A | 2019-04-05 | APR | 2019 | 2019-02-28
Owner2 | Owner6 | LOA | BCD System | IS004963 | Data definitions | 2020-12-31 |  |  | In progress | N/A | 2020-12-31 | DEC | 2020 | 2019-02-28
Owner2 | Owner6 | LOA | BCD System | IS004964 | Data definitions | 2019-12-31 |  |  | Open Issue Need to Close Out | Non-CCAR | 2019-12-31 | DEC | 2019 | 2019-02-28
Owner2 | Owner4 | LOA | BCD System | IS004965 | Data definitions | 2018-01-08 |  |  | Open Issue Need to Close Out | Non-CCAR | 2018-01-08 | JAN | 2018 | 2019-02-28
Owner2 | Owner4 | LOA | BCD System | IS004966 | Data definitions | 2018-01-31 |  |  | Open Issue Need to Close Out | CCAR | 2018-01-31 | JAN | 2018 | 2019-02-28
Owner3 | Owner4 | LOA | BCD System | IS004967 | Data definitions | 2019-10-30 |  |  | Open Issue Need to Close Out | N/A | 2019-10-30 | OCT | 2019 | 2019-02-28
Owner3 | Owner1 | GGG | BCD System | IS004968 | Data definitions | 2019-10-30 |  |  | Open Issue Need to Close Out | N/A | 2019-10-30 | OCT | 2019 | 2019-02-28
Owner3 | Owner1 | GGG | BCD System | IS004969 | Data definitions | 2018-12-03 |  | Type 3 - Moderate | Open Issue Need to Close Out | N/A | 2018-12-03 | DEC | 2018 | 2019-02-28
Owner3 | Owner1 | GGG | BCD System | IS004970 | Data definitions | 2018-12-03 |  | Type 3 - Moderate | In progress | Non-CCAR | 2018-12-03 | DEC | 2018 | 2019-02-28
Owner3 | Owner2 | GGG | BCD System | IS004971 | Data definitions | 2019-09-30 |  | Type 2 - High | In progress | Non-CCAR | 2019-09-30 | SEP | 2019 | 2019-02-28
Owner3 | Owner3 | FFF | BCD System | IS004972 | Data definitions | 2019-08-31 |  | Type 3 - Moderate | In progress | CCAR | 2019-08-31 | AUG | 2019 | 2019-02-28
Owner3 | Owner3 | HHH | BCD System | IS004973 | Data definitions | 2019-08-31 |  | Type 3 - Moderate | Open Issue Need to Close Out | Non-CCAR | 2019-08-31 | AUG | 2019 | 2019-02-28
Owner3 | Owner3 | HHH | BCD System | IS004974 | Data definitions | 2020-02-28 |  | Type 3 - Moderate | Open Issue Need to Close Out | Non-CCAR | 2020-02-28 | FEB | 2020 | 2019-02-28
Owner3 | Owner3 | HHH | BCD System | IS004975 | Data definitions | 2019-08-31 |  | Type 3 - Moderate | Open Issue Need to Close Out | Non-CCAR | 2019-08-31 | AUG | 2019 | 2019-02-28
Owner3 | Owner2 | AAA | BCD System | IS004976 | Data definitions | 2019-09-30 |  | Type 3 - Moderate | Open Issue Need to Close Out | Non-CCAR | 2019-09-30 | SEP | 2019 | 2019-02-28
Owner3 | Owner4 | AAA | BCD System | IS004977 | Data definitions | 2020-03-31 |  | Type 3 - Moderate | Open Issue Need to Close Out | Non-CCAR | 2020-03-31 | MAR | 2020 | 2019-02-28
Owner3 | Owner5 | AAA | BCD System | IS004978 | Data definitions | 2020-03-31 |  | Type 3 - Moderate | Open Issue Need to Close Out | Non-CCAR | 2020-03-31 | MAR | 2020 | 2019-02-28
Owner4 | Owner6 | AAA | BCD System | IS004979 | Data definitions | 2020-03-31 |  | Type 1 - Critical | Open Issue Need to Close Out | Non-CCAR | 2020-03-31 | MAR | 2020 | 2019-02-28
Owner4 | Owner6 | MAR | BCD System | IS004980 | Data definitions | 2019-08-31 |  | Type 3 - Moderate | Open Issue Need to Close Out | Non-CCAR | 2019-08-31 | AUG | 2019 | 2019-02-28
Owner4 | Owner1 | MAR | BCD System | IS004981 | Data definitions | 2019-03-29 |  | Type 3 - Moderate | In progress | Non-CCAR | 2019-03-29 | MAR | 2019 | 2019-02-28
Owner4 | Owner1 | MAR | BCD System | IS004982 | Data definitions | 2019-06-28 |  | Type 3 - Moderate | In progress | Non-CCAR | 2019-06-28 | JUN | 2019 | 2019-02-28
Owner4 | Owner2 | GGG | BCD System | IS004983 | Data definitions | 2019-05-23 |  | Type 3 - Moderate | In progress | Non-CCAR | 2019-05-23 | MAY | 2019 | 2019-02-28
Owner4 | Owner3 | SMA | BCD System | IS004984 | Data definitions | 2018-10-31 |  | Type 3 - Moderate | In progress | Non-CCAR | 2018-10-31 | OCT | 2018 | 2019-02-28
Owner4 | Owner3 | SMA | BCD System | IS004985 | Data definitions | 2018-07-31 |  | Type 3 - Moderate | In progress | Non-CCAR | 2018-07-31 | JUL | 2018 | 2019-02-28
Owner4 | Owner1 | ALL | BCD System | IS004986 | Data definitions | 2018-10-31 |  | Type 1 - Critical | In progress | Non-CCAR | 2018-10-31 | OCT | 2018 | 2019-02-28
Owner4 | Owner2 | ALL | BCD System | IS004987 | Data definitions | 2019-09-29 |  | Type 3 - Moderate | In progress | Non-CCAR | 2019-09-29 | SEP | 2019 | 2019-02-28
Owner4 | Owner3 | CCC | BCD System | IS004988 | Data definitions | 2019-09-30 |  |  | In progress | Non-CCAR | 2019-09-30 | SEP | 2019 | 2019-02-28
Owner4 | Owner4 | DDD | BCD System | IS004989 | Data definitions | 2019-09-30 |  |  | In progress | Non-CCAR | 2019-09-30 | SEP | 2019 | 2019-02-28
Owner4 | Owner4 | BBB | BCD System | IS004990 | Data definitions | 2019-09-30 |  |  | In progress | Non-CCAR | 2019-09-30 | SEP | 2019 | 2019-02-28
Owner4 | Owner4 | RIH | BCD System | IS004991 | Data definitions | 2018-09-28 |  |  | In progress | N/A | 2018-09-28 | SEP | 2018 | 2019-02-28
Owner4 | Owner3 | RIH | BCD System | IS004992 | Data definitions | 2019-03-31 |  |  | In progress | N/A | 2019-03-31 | MAR | 2019 | 2019-02-28
Owner4 | Owner3 | EPN | BCD System | IS004993 | Data definitions | 2019-03-31 |  |  | In progress | N/A | 2019-03-31 | MAR | 2019 | 2019-02-28
Owner4 | Owner3 | OPS | BCD System | IS004994 | Data definitions | 2019-06-30 |  |  | In progress | N/A | 2019-06-30 | JUN | 2019 | 2019-02-28
Owner4 | Owner3 | LOA | BCD System | IS004995 | Data definitions | 2019-11-29 |  |  | In progress | N/A | 2019-11-29 | NOV | 2019 | 2019-02-28
Owner4 | Owner2 | GGG | BCD System | IS004996 | Data definitions | 2019-11-29 |  |  | In progress | N/A | 2019-11-29 | NOV | 2019 | 2019-02-28
Owner4 | Owner4 | GGG | BCD System | IS004997 | Data definitions | 2017-12-31 |  |  | In progress | N/A | 2017-12-31 | DEC | 2017 | 2019-02-28
Owner4 | Owner1 | PPN | BCD System | IS004998 | Data definitions | 2019-09-29 |  |  | In progress | N/A | 2019-09-29 | SEP | 2019 | 2019-02-28
Owner4 | Owner2 | PPN | BCD System | IS004999 | Data definitions | 2019-09-30 |  |  | In progress | N/A | 2019-09-30 | SEP | 2019 | 2019-02-28
Owner4 | Owner3 | PPN | BCD System | IS005000 | Data definitions | 2019-09-30 |  |  | In progress | N/A | 2019-09-30 | SEP | 2019 | 2019-02-28
Owner4 | Owner4 | PPN | BCD System | IS005001 | Data definitions | 2019-09-30 |  |  | In progress | N/A | 2019-09-30 | SEP | 2019 | 2019-02-28
Owner4 | Owner5 | PPN | BCD System | IS005002 | Data definitions | 2018-09-28 |  |  | In progress | N/A | 2018-09-28 | SEP | 2018 | 2019-02-28
Owner4 | Owner5 | PPN | BCD System | IS005003 | Data definitions | 2019-03-31 |  |  | In progress | N/A | 2019-03-31 | MAR | 2019 | 2019-02-28
Owner4 | Owner5 | PPN | BCD System | IS005004 | Data definitions | 2019-03-31 |  |  | In progress | N/A | 2019-03-31 | MAR | 2019 | 2019-02-28
Owner4 | Owner4 | PPN | BCD System | IS005005 | Data definitions | 2019-06-30 |  | Type 3 - Moderate | In progress | N/A | 2019-06-30 | JUN | 2019 | 2019-02-28
Owner4 | Owner4 | BBB | BCD System | IS005006 | Data definitions | 2019-11-29 |  | Type 3 - Moderate | In progress | N/A | 2019-11-29 | NOV | 2019 | 2019-02-28
Owner4 | Owner4 | POL | BCD System | IS005007 | Data definitions | 2019-11-29 |  | Type 3 - Moderate | In progress | N/A | 2019-11-29 | NOV | 2019 | 2019-02-28
Owner4 | Owner3 | BBB | BCD System | IS005008 | Data definitions | 2019-10-30 |  | Type 2 - High | In progress | N/A | 2019-10-30 | OCT | 2019 | 2019-02-28
Owner4 | Owner5 | BBB | BCD System | IS005009 | Data definitions | 2018-12-03 |  | Type 2 - High | In progress | N/A | 2018-12-03 | DEC | 2018 | 2019-02-28
Owner4 | Owner6 | BBB | BCD System | IS005010 | Data definitions | 2018-12-03 | 2020-12-31 |  | In progress | Non-CCAR | 2020-12-31 | DEC | 2020 | 2019-02-28
Owner4 | Owner6 | BBB | BCD System | IS005011 | Data definitions | 2019-09-30 | 2020-12-31 |  | In progress | Non-CCAR | 2020-12-31 | DEC | 2020 | 2019-02-28
Owner4 | Owner1 | POL | BCD System | IS005012 | Data definitions | 2019-08-31 |  |  | In progress | Non-CCAR | 2019-08-31 | AUG | 2019 | 2019-02-28
Owner4 | Owner1 | POL | BCD System | IS005013 | Data definitions | 2019-08-31 |  |  | In progress | Non-CCAR | 2019-08-31 | AUG | 2019 | 2019-02-28
Owner4 | Owner2 | POL | BCD System | IS005014 | Data definitions | 2020-03-31 |  |  | In progress | Non-CCAR | 2020-03-31 | MAR | 2020 | 2019-02-28
Owner4 | Owner3 | GGG | BCD System | IS005015 | Data definitions | 2019-08-31 |  |  | In progress | CCAR | 2019-08-31 | AUG | 2019 | 2019-02-28
Owner4 | Owner3 | FFF | BCD System | 1 | Data definitions | 2019-03-29 |  | Type 2 - High | In progress | CCAR | 2019-03-29 | MAR | 2019 | 2019-02-28
Owner4 | Owner1 | HHH | BCD System | 2 | Data definitions | 2019-06-28 |  |  | In progress | CCAR | 2019-06-28 | JUN | 2019 | 2019-02-28
Owner4 | Owner2 | HHH | BCD System | 3 | Data definitions | 2019-05-23 |  |  | In progress | CCAR | 2019-05-23 | MAY | 2019 | 2019-02-28
Owner4 | Owner3 | HHH | BCD System | 4 | Data definitions | 2018-10-31 |  |  | In progress | CCAR | 2018-10-31 | OCT | 2018 | 2019-02-28
Owner4 | Owner4 | AAA | BCD System | 5 | Data definitions | 2018-10-31 | 2019-05-31 | Type 2 - High | In progress | N/A | 2019-05-31 | MAY | 2019 | 2019-02-28
Owner5 | Owner5 | AAA | BCD System | 6 | Data definitions | 2018-10-31 | 1899-12-31 |  | In progress | N/A | 1899-12-31 | JAN | 1900 | 2019-02-28
Owner5 | Owner4 | AAA | BCD System | 7 | Data definitions | 2019-11-30 | 2019-03-31 |  | In progress | Non-CCAR | 2019-03-31 | MAR | 2019 | 2019-02-28
Owner5 | Owner1 | AAA | BCD System | 8 | Data definitions | 2019-11-30 | 2019-03-31 |  | In progress | Non-CCAR | 2019-03-31 | MAR | 2019 | 2019-02-28
Owner5 | Owner2 | MAR | BCD System | 9 | Data definitions | 2019-10-30 | 2019-03-31 | Type 3 - Moderate | In progress | N/A | 2019-03-31 | MAR | 2019 | 2019-02-28
Owner5 | Owner3 | MAR | BCD System | 10 | Data definitions | 2018-12-03 |  | Type 3 - Moderate | In progress | N/A | 2018-12-03 | DEC | 2018 | 2019-02-28
Owner5 | Owner4 | MAR | BCD System | 11 | Data definitions | 2018-12-03 |  | Type 3 - Moderate | In progress | Non-CCAR | 2018-12-03 | DEC | 2018 | 2019-02-28
Owner5 | Owner5 | GGG | BCD System | 12 | Data definitions | 2019-09-30 |  | Type 3 - Moderate | In progress | Non-CCAR | 2019-09-30 | SEP | 2019 | 2019-02-28
Owner5 | Owner5 | SMA | BCD System | 13 | Data definitions | 2019-08-31 |  | Type 3 - Moderate | In progress | N/A | 2019-08-31 | AUG | 2019 | 2019-02-28
Owner5 | Owner4 | WHO | EFG System | ISS_012579 | Data definitions | 2019-08-31 |  | Type 1 - Critical | In progress | N/A | 2019-08-31 | AUG | 2019 | 2019-02-28
Owner5 | Owner3 | WHO | FGH System | ISS_012580 | Data definitions | 2019-10-31 |  |  | In progress | N/A | 2019-10-31 | OCT | 2019 | 2019-02-28
Owner5 | Owner1 | WHO | FGH System | ISS_012581 | Data definitions | 2019-10-31 | 2019-06-28 |  | In progress | N/A | 2019-06-28 | JUN | 2019 | 2019-02-28
Owner5 | Owner1 | WHO | FGH System | ISS_012582 | Data definitions | 2019-10-31 | 2019-03-31 |  | In progress | N/A | 2019-03-31 | MAR | 2019 | 2019-02-28
Owner6 | Owner2 | OPS | FGH System | ISS_012583 | Data definitions | 2019-10-31 | 2019-05-01 |  | In progress | N/A | 2019-05-01 | MAY | 2019 | 2019-02-28
Owner6 | Owner3 | HEL | EFG System | ISS_012584 | Data definitions | 2018-09-30 | 2025-12-31 |  | In progress | N/A | 2025-12-31 | DEC | 2025 | 2019-02-28
Owner6 | Owner3 | IFR | FGH System | ISS_012585 | Data definitions | 2019-05-23 | 2020-12-31 | Type 1 - Critical | In progress | N/A | 2020-12-31 | DEC | 2020 | 2019-02-28
Owner6 | Owner1 | IFR | FGH System | ISS_012586 | Data definitions | 2019-03-29 | 2019-12-31 |  | In progress | CCAR | 2019-12-31 | DEC | 2019 | 2019-02-28
Owner6 | Owner1 | OPT | FGH System | ISS_012587 | Data definitions | 2018-09-30 | 2019-03-31 |  | In progress | CCAR | 2019-03-31 | MAR | 2019 | 2019-02-28
Owner6 | Owner3 | RBC | FGH System | ISS_012588 | Data definitions | 2019-05-23 | 2019-03-31 |  | In progress | CCAR | 2019-03-31 | MAR | 2019 | 2019-02-28
Owner1 | Owner2 | SEL | ABC System | 93 | Data definitions | 2020-12-31 | 2019-06-28 | Type 3 - Moderate | In progress | CCAR | 2019-06-28 | JUN | 2019 | 2019-03-31
Owner1 | Owner4 | GEL | ABC System | ISSUE-00001116 | Data definitions | 2020-12-31 | 2019-03-31 | Type 3 - Moderate | In progress | CCAR | 2019-03-31 | MAR | 2019 | 2019-03-31
Owner1 | Owner4 | GEL | ABC System | ISSUE-00001117 | Data definitions | 2019-03-31 | 2019-05-01 | Type 2 - High | In progress | CCAR | 2019-05-01 | MAY | 2019 | 2019-03-31
Owner1 | Owner4 | SEL | ABC System | ISSUE-00001119 | Data definitions | 2019-06-30 | 2020-12-31 | Type 2 - High | In progress | CCAR | 2020-12-31 | DEC | 2020 | 2019-03-31
Owner1 | Owner4 | SEL | ABC System | 1040 | Data definitions | 2019-11-01 | 2019-12-31 | Type 1 - Critical | In progress | CCAR | 2019-12-31 | DEC | 2019 | 2019-03-31
Owner1 | Owner1 | SEL | ABC System | 1075 | Data definitions | 2019-10-30 | 2019-03-31 | Type 3 - Moderate | In progress | Non-CCAR | 2019-03-31 | MAR | 2019 | 2019-03-31
Owner1 | Owner1 | SEL | BCD System | 1162 | Data definitions | 2019-04-05 | 2019-03-31 | Type 2 - High | In progress | Non-CCAR | 2019-03-31 | MAR | 2019 | 2019-03-31
Owner1 | Owner1 | SEL | DEF System | 1253 | Data definitions | 2020-12-31 |  | Type 2 - High | In progress | Non-CCAR | 2020-12-31 | DEC | 2020 | 2019-03-31
Owner1 | Owner2 | SEL | DEF System | 1301 | Data definitions | 2019-12-31 |  |  | In progress | Non-CCAR | 2019-12-31 | DEC | 2019 | 2019-03-31
Owner1 | Owner3 | SEL | DEF System | 1077 | Data definitions | 2018-01-08 |  |  | In progress | Non-CCAR | 2018-01-08 | JAN | 2018 | 2019-03-31
Owner1 | Owner3 | SEL | DEF System | 1302 | Data definitions | 2018-01-31 |  |  | In progress | Non-CCAR | 2018-01-31 | JAN | 2018 | 2019-03-31
Owner1 | Owner3 | SEL | DEF System | 1260 | Data definitions | 2019-10-30 |  |  | In progress | Non-CCAR | 2019-10-30 | OCT | 2019 | 2019-03-31
Owner1 | Owner3 | SEL | CDE System | 1281 | Data definitions | 2019-10-30 |  |  | In progress | Non-CCAR | 2019-10-30 | OCT | 2019 | 2019-03-31
Owner1 | Owner2 | SEL | CDE System | IS003447 | Data definitions | 2018-12-03 |  |  | In progress | Non-CCAR | 2018-12-03 | DEC | 2018 | 2019-03-31
Owner1 | Owner4 | GEL | CDE System | IS003448 | Data definitions | 2018-12-03 |  |  | In progress | Non-CCAR | 2018-12-03 | DEC | 2018 | 2019-03-31
Owner1 | Owner4 | GEL | CDE System | IS003449 | Data definitions | 2019-09-30 |  | Type 3 - Moderate | In progress | N/A | 2019-09-30 | SEP | 2019 | 2019-03-31
Owner1 | Owner4 | GEL | CDE System | IS003450 | Data definitions | 2019-08-31 |  | Type 3 - Moderate | Open Issue Need to Close Out | N/A | 2019-08-31 | AUG | 2019 | 2019-03-31
Owner1 | Owner3 | LEN | CDE System | IS003451 | Data definitions | 2019-08-31 |  | Type 3 - Moderate | In progress | N/A | 2019-08-31 | AUG | 2019 | 2019-03-31
Owner1 | Owner3 | LEN | CDE System | IS003452 | Data definitions | 2020-02-28 |  | Type 2 - High | In progress | N/A | 2020-02-28 | FEB | 2020 | 2019-03-31
Owner1 | Owner3 | LEN | CDE System | FND-139 | Data definitions | 2019-08-31 |  | Type 2 - High | In progress | N/A | 2019-08-31 | AUG | 2019 | 2019-03-31
Owner1 | Owner2 | RDC | CDE System | FND-141 | Data definitions | 2020-03-31 |  | Type 2 - High | In progress | N/A | 2020-03-31 | MAR | 2020 | 2019-03-31
Owner1 | Owner4 | RDC | CDE System | FND-142 | Data definitions | 2020-03-31 |  |  | Open Issue Need to Close Out | N/A | 2020-03-31 | MAR | 2020 | 2019-03-31
Owner1 | Owner1 | FFF | CDE System | FND-143 | Data definitions | 2020-03-31 |  |  | Open Issue Need to Close Out | N/A | 2020-03-31 | MAR | 2020 | 2019-03-31
Owner1 | Owner2 | EEE | CDE System | FND-144 | Data definitions | 2019-08-31 |  |  | Open Issue Need to Close Out | N/A | 2019-08-31 | AUG | 2019 | 2019-03-31
Owner1 | Owner3 | EEE | BCD System | FND-145 | Data definitions | 2019-09-30 |  | Type 2 - High | Open Issue Need to Close Out | N/A | 2019-09-30 | SEP | 2019 | 2019-03-31
Owner2 | Owner4 | GGG | BCD System | FND-146 | Data definitions | 2018-12-31 |  | Type 2 - High | Open Issue Need to Close Out | N/A | 2018-12-31 | DEC | 2018 | 2019-03-31
Owner2 | Owner5 | EEE | BCD System | FND-147 | Data definitions | 2019-10-30 | 2019-08-15 | Type 2 - High | Open Issue Need to Close Out | N/A | 2019-08-15 | AUG | 2019 | 2019-03-31
Owner2 | Owner5 | SEL | BCD System | FND-148 | Data definitions | 2019-06-01 | 2019-08-15 | Type 3 - Moderate | Open Issue Need to Close Out | N/A | 2019-08-15 | AUG | 2019 | 2019-03-31
Owner2 | Owner5 | SEL | BCD System | FND-149 | Data definitions | 2019-09-30 | 2019-08-15 |  | Open Issue Need to Close Out | N/A | 2019-08-15 | AUG | 2019 | 2019-03-31
Owner2 | Owner5 | EEE | BCD System | FND-147 | Data definitions | 2019-10-30 | 2019-08-15 | Type 2 - High | Open Issue Need to Close Out | N/A | 2019-08-15 | AUG | 2019 | 2019-03-31
Owner2 | Owner6 | LOA | BCD System | IS004964 | Data definitions | 2019-12-31 |  |  | Open Issue Need to Close Out | Non-CCAR | 2019-12-31 | DEC | 2019 | 2019-03-31
Owner2 | Owner4 | SEL | BCD System | IS004958 | Data definitions | 2018-10-30 | 2020-03-30 |  | Open Issue Need to Close Out | N/A | 2020-03-30 | MAR | 2020 | 2019-03-31
Owner2 | Owner4 | SEL | BCD System | IS004959 | Data definitions | 2019-01-31 | 2018-09-28 |  | In progress | N/A | 2018-09-28 | SEP | 2018 | 2019-03-31
Owner2 | Owner4 | SEL | BCD System | IS004960 | Data definitions | 2019-11-01 | 2018-09-28 |  | In progress | N/A | 2018-09-28 | SEP | 2018 | 2019-03-31
Owner2 | Owner3 | SEL | BCD System | IS004961 | Data definitions | 2019-10-30 | 2019-03-31 |  | Open Issue Need to Close Out | N/A | 2019-03-31 | MAR | 2019 | 2019-03-31
Owner2 | Owner5 | GGG | BCD System | IS004962 | Data definitions | 2019-04-05 |  | Type 1 - Critical | In progress | N/A | 2019-04-05 | APR | 2019 | 2019-03-31
Owner2 | Owner6 | LOA | BCD System | IS004963 | Data definitions | 2020-12-31 |  |  | In progress | N/A | 2020-12-31 | DEC | 2020 | 2019-03-31
Owner2 | Owner6 | LOA | BCD System | IS004964 | Data definitions | 2019-12-31 |  |  | Open Issue Need to Close Out | Non-CCAR | 2019-12-31 | DEC | 2019 | 2019-03-31
Owner2 | Owner4 | LOA | BCD System | IS004965 | Data definitions | 2018-01-08 |  |  | Open Issue Need to Close Out | Non-CCAR | 2018-01-08 | JAN | 2018 | 2019-03-31
Owner2 | Owner4 | LOA | BCD System | IS004966 | Data definitions | 2018-01-31 |  |  | Open Issue Need to Close Out | CCAR | 2018-01-31 | JAN | 2018 | 2019-03-31
Owner3 | Owner4 | LOA | BCD System | IS004967 | Data definitions | 2019-10-30 |  |  | Open Issue Need to Close Out | N/A | 2019-10-30 | OCT | 2019 | 2019-03-31
Owner3 | Owner1 | GGG | BCD System | IS004968 | Data definitions | 2019-10-30 |  |  | Open Issue Need to Close Out | N/A | 2019-10-30 | OCT | 2019 | 2019-03-31
Owner3 | Owner1 | GGG | BCD System | IS004969 | Data definitions | 2018-12-03 |  | Type 3 - Moderate | Open Issue Need to Close Out | N/A | 2018-12-03 | DEC | 2018 | 2019-03-31
Owner3 | Owner1 | GGG | BCD System | IS004970 | Data definitions | 2018-12-03 |  | Type 3 - Moderate | In progress | Non-CCAR | 2018-12-03 | DEC | 2018 | 2019-03-31
Owner3 | Owner2 | GGG | BCD System | IS004971 | Data definitions | 2019-09-30 |  | Type 2 - High | In progress | Non-CCAR | 2019-09-30 | SEP | 2019 | 2019-03-31
Owner3 | Owner1 | GGG | BCD System | IS004970 | Data definitions | 2018-12-03 |  | Type 3 - Moderate | In progress | Non-CCAR | 2018-12-03 | DEC | 2018 | 2019-03-31
Owner3 | Owner3 | FFF | BCD System | IS004972 | Data definitions | 2019-08-31 |  | Type 3 - Moderate | In progress | CCAR | 2019-08-31 | AUG | 2019 | 2019-03-31
Owner3 | Owner3 | HHH | BCD System | IS004973 | Data definitions | 2019-08-31 |  | Type 3 - Moderate | Open Issue Need to Close Out | Non-CCAR | 2019-08-31 | AUG | 2019 | 2019-03-31
Owner3 | Owner3 | HHH | BCD System | IS004974 | Data definitions | 2020-02-28 |  | Type 3 - Moderate | Open Issue Need to Close Out | Non-CCAR | 2020-02-28 | FEB | 2020 | 2019-03-31
Owner3 | Owner3 | HHH | BCD System | IS004975 | Data definitions | 2019-08-31 |  | Type 3 - Moderate | Open Issue Need to Close Out | Non-CCAR | 2019-08-31 | AUG | 2019 | 2019-03-31
Owner3 | Owner2 | AAA | BCD System | IS004976 | Data definitions | 2019-09-30 |  | Type 3 - Moderate | Open Issue Need to Close Out | Non-CCAR | 2019-09-30 | SEP | 2019 | 2019-03-31
Owner3 | Owner4 | AAA | BCD System | IS004977 | Data definitions | 2020-03-31 |  | Type 3 - Moderate | Open Issue Need to Close Out | Non-CCAR | 2020-03-31 | MAR | 2020 | 2019-03-31
Owner3 | Owner5 | AAA | BCD System | IS004978 | Data definitions | 2020-03-31 |  | Type 3 - Moderate | Open Issue Need to Close Out | Non-CCAR | 2020-03-31 | MAR | 2020 | 2019-03-31
Owner4 | Owner6 | AAA | BCD System | IS004979 | Data definitions | 2020-03-31 |  | Type 1 - Critical | Open Issue Need to Close Out | Non-CCAR | 2020-03-31 | MAR | 2020 | 2019-03-31
Owner4 | Owner6 | MAR | BCD System | IS004980 | Data definitions | 2019-08-31 |  | Type 3 - Moderate | Open Issue Need to Close Out | Non-CCAR | 2019-08-31 | AUG | 2019 | 2019-03-31
Owner4 | Owner1 | MAR | BCD System | IS004981 | Data definitions | 2019-03-29 |  | Type 3 - Moderate | In progress | Non-CCAR | 2019-03-29 | MAR | 2019 | 2019-03-31
Owner4 | Owner1 | MAR | BCD System | IS004982 | Data definitions | 2019-06-28 |  | Type 3 - Moderate | In progress | Non-CCAR | 2019-06-28 | JUN | 2019 | 2019-03-31
Owner4 | Owner2 | GGG | BCD System | IS004983 | Data definitions | 2019-05-23 |  | Type 3 - Moderate | In progress | Non-CCAR | 2019-05-23 | MAY | 2019 | 2019-03-31
Owner4 | Owner3 | SMA | BCD System | IS004984 | Data definitions | 2018-10-31 |  | Type 3 - Moderate | In progress | Non-CCAR | 2018-10-31 | OCT | 2018 | 2019-03-31
Owner4 | Owner3 | SMA | BCD System | IS004985 | Data definitions | 2018-07-31 |  | Type 3 - Moderate | In progress | Non-CCAR | 2018-07-31 | JUL | 2018 | 2019-03-31
Owner4 | Owner1 | ALL | BCD System | IS004986 | Data definitions | 2018-10-31 |  | Type 1 - Critical | In progress | Non-CCAR | 2018-10-31 | OCT | 2018 | 2019-03-31
Owner4 | Owner2 | ALL | BCD System | IS004987 | Data definitions | 2019-09-29 |  | Type 3 - Moderate | In progress | Non-CCAR | 2019-09-29 | SEP | 2019 | 2019-03-31
Owner4 | Owner3 | DDD | BCD System | IS004988 | Data definitions | 2019-09-30 |  |  | In progress | Non-CCAR | 2019-09-30 | SEP | 2019 | 2019-03-31
Owner4 | Owner4 | DDD | BCD System | IS004989 | Data definitions | 2019-09-30 |  |  | In progress | Non-CCAR | 2019-09-30 | SEP | 2019 | 2019-03-31
Owner4 | Owner4 | BBB | BCD System | IS004990 | Data definitions | 2019-09-30 |  |  | In progress | Non-CCAR | 2019-09-30 | SEP | 2019 | 2019-03-31
Owner4 | Owner4 | RIH | BCD System | IS004991 | Data definitions | 2018-09-28 |  |  | In progress | N/A | 2018-09-28 | SEP | 2018 | 2019-03-31
Owner4 | Owner3 | RIH | BCD System | IS004992 | Data definitions | 2019-03-31 |  |  | In progress | N/A | 2019-03-31 | MAR | 2019 | 2019-03-31
Owner4 | Owner3 | EPN | BCD System | IS004993 | Data definitions | 2019-03-31 |  |  | In progress | N/A | 2019-03-31 | MAR | 2019 | 2019-03-31
Owner4 | Owner3 | OPS | BCD System | IS004994 | Data definitions | 2019-06-30 |  |  | In progress | N/A | 2019-06-30 | JUN | 2019 | 2019-03-31
Owner4 | Owner3 | LOA | BCD System | IS004995 | Data definitions | 2019-11-29 |  |  | In progress | N/A | 2019-11-29 | NOV | 2019 | 2019-03-31
Owner4 | Owner2 | GGG | BCD System | IS004996 | Data definitions | 2019-11-29 |  |  | In progress | N/A | 2019-11-29 | NOV | 2019 | 2019-03-31
Owner4 | Owner4 | GGG | BCD System | IS004997 | Data definitions | 2017-12-31 |  |  | In progress | N/A | 2017-12-31 | DEC | 2017 | 2019-03-31
Owner4 | Owner1 | PPN | BCD System | IS004998 | Data definitions | 2019-09-29 |  |  | In progress | N/A | 2019-09-29 | SEP | 2019 | 2019-03-31
Owner4 | Owner2 | PPN | BCD System | IS004999 | Data definitions | 2019-09-30 |  |  | In progress | N/A | 2019-09-30 | SEP | 2019 | 2019-03-31
Owner4 | Owner3 | PPN | BCD System | IS005000 | Data definitions | 2019-09-30 |  |  | In progress | N/A | 2019-09-30 | SEP | 2019 | 2019-03-31
Owner4 | Owner4 | PPN | BCD System | IS005001 | Data definitions | 2019-09-30 |  |  | In progress | N/A | 2019-09-30 | SEP | 2019 | 2019-03-31
Owner4 | Owner5 | PPN | BCD System | IS005002 | Data definitions | 2018-09-28 |  |  | In progress | N/A | 2018-09-28 | SEP | 2018 | 2019-03-31
Owner4 | Owner5 | PPN | BCD System | IS005003 | Data definitions | 2019-03-31 |  |  | In progress | N/A | 2019-03-31 | MAR | 2019 | 2019-03-31
Owner4 | Owner5 | PPN | BCD System | IS005004 | Data definitions | 2019-03-31 |  |  | In progress | N/A | 2019-03-31 | MAR | 2019 | 2019-03-31
Owner4 | Owner4 | PPN | BCD System | IS005005 | Data definitions | 2019-06-30 |  | Type 3 - Moderate | In progress | N/A | 2019-06-30 | JUN | 2019 | 2019-03-31
Owner4 | Owner4 | BBB | BCD System | IS005006 | Data definitions | 2019-11-29 |  | Type 3 - Moderate | In progress | N/A | 2019-11-29 | NOV | 2019 | 2019-03-31
Owner4 | Owner4 | POL | BCD System | IS005007 | Data definitions | 2019-11-29 |  | Type 3 - Moderate | In progress | N/A | 2019-11-29 | NOV | 2019 | 2019-03-31
Owner4 | Owner3 | BBB | BCD System | IS005008 | Data definitions | 2019-10-30 |  | Type 2 - High | In progress | N/A | 2019-10-30 | OCT | 2019 | 2019-03-31
Owner4 | Owner5 | BBB | BCD System | IS005009 | Data definitions | 2018-12-03 |  | Type 2 - High | In progress | N/A | 2018-12-03 | DEC | 2018 | 2019-03-31
Owner4 | Owner6 | BBB | BCD System | IS005010 | Data definitions | 2018-12-03 | 2020-12-31 |  | In progress | Non-CCAR | 2020-12-31 | DEC | 2020 | 2019-03-31
Owner4 | Owner6 | BBB | BCD System | IS005011 | Data definitions | 2019-09-30 | 2020-12-31 |  | In progress | Non-CCAR | 2020-12-31 | DEC | 2020 | 2019-03-31
Owner4 | Owner1 | POL | BCD System | IS005012 | Data definitions | 2019-08-31 |  |  | In progress | Non-CCAR | 2019-08-31 | AUG | 2019 | 2019-03-31
Owner4 | Owner1 | POL | BCD System | IS005013 | Data definitions | 2019-08-31 |  |  | In progress | Non-CCAR | 2019-08-31 | AUG | 2019 | 2019-03-31
Owner4 | Owner2 | POL | BCD System | IS005014 | Data definitions | 2020-03-31 |  |  | In progress | Non-CCAR | 2020-03-31 | MAR | 2020 | 2019-03-31
Owner4 | Owner3 | GGG | BCD System | IS005015 | Data definitions | 2019-08-31 |  |  | In progress | CCAR | 2019-08-31 | AUG | 2019 | 2019-03-31
Owner4 | Owner3 | FFF | BCD System | 1 | Data definitions | 2019-03-29 |  | Type 2 - High | In progress | CCAR | 2019-03-29 | MAR | 2019 | 2019-03-31
Owner4 | Owner1 | HHH | BCD System | 2 | Data definitions | 2019-06-28 |  |  | In progress | CCAR | 2019-06-28 | JUN | 2019 | 2019-03-31
Owner4 | Owner2 | HHH | BCD System | 3 | Data definitions | 2019-05-23 |  |  | In progress | CCAR | 2019-05-23 | MAY | 2019 | 2019-03-31
Owner4 | Owner3 | HHH | BCD System | 4 | Data definitions | 2018-10-31 |  |  | In progress | CCAR | 2018-10-31 | OCT | 2018 | 2019-03-31
Owner4 | Owner4 | AAA | BCD System | 5 | Data definitions | 2018-10-31 | 2019-05-31 | Type 2 - High | In progress | N/A | 2019-05-31 | MAY | 2019 | 2019-03-31
Owner5 | Owner5 | AAA | BCD System | 6 | Data definitions | 2018-10-31 | 1899-12-31 |  | In progress | N/A | 1899-12-31 | JAN | 1900 | 2019-03-31
Owner5 | Owner4 | AAA | BCD System | 7 | Data definitions | 2019-11-30 | 2019-03-31 |  | In progress | Non-CCAR | 2019-03-31 | MAR | 2019 | 2019-03-31
Owner5 | Owner1 | AAA | BCD System | 8 | Data definitions | 2019-11-30 | 2019-03-31 |  | In progress | Non-CCAR | 2019-03-31 | MAR | 2019 | 2019-03-31
Owner5 | Owner2 | MAR | BCD System | 9 | Data definitions | 2019-10-30 | 2019-03-31 | Type 3 - Moderate | In progress | N/A | 2019-03-31 | MAR | 2019 | 2019-03-31
Owner5 | Owner3 | MAR | BCD System | 10 | Data definitions | 2018-12-03 |  | Type 3 - Moderate | In progress | N/A | 2018-12-03 | DEC | 2018 | 2019-03-31
Owner5 | Owner4 | MAR | BCD System | 11 | Data definitions | 2018-12-03 |  | Type 3 - Moderate | In progress | Non-CCAR | 2018-12-03 | DEC | 2018 | 2019-03-31
Owner5 | Owner5 | GGG | BCD System | 12 | Data definitions | 2019-09-30 |  | Type 3 - Moderate | In progress | Non-CCAR | 2019-09-30 | SEP | 2019 | 2019-03-31
Owner5 | Owner5 | SMA | BCD System | 13 | Data definitions | 2019-08-31 |  | Type 3 - Moderate | In progress | N/A | 2019-08-31 | AUG | 2019 | 2019-03-31
Owner5 | Owner4 | WHO | EFG System | ISS_012579 | Data definitions | 2019-08-31 |  | Type 1 - Critical | In progress | N/A | 2019-08-31 | AUG | 2019 | 2019-03-31
Owner5 | Owner3 | WHO | FGH System | ISS_012580 | Data definitions | 2019-10-31 |  |  | In progress | N/A | 2019-10-31 | OCT | 2019 | 2019-03-31
Owner5 | Owner1 | WHO | FGH System | ISS_012581 | Data definitions | 2019-10-31 | 2019-06-28 |  | In progress | N/A | 2019-06-28 | JUN | 2019 | 2019-03-31
Owner5 | Owner1 | WHO | FGH System | ISS_012582 | Data definitions | 2019-10-31 | 2019-03-31 |  | In progress | N/A | 2019-03-31 | MAR | 2019 | 2019-03-31
Owner6 | Owner2 | HEL | FGH System | ISS_012583 | Data definitions | 2019-10-31 | 2019-05-01 |  | In progress | N/A | 2019-05-01 | MAY | 2019 | 2019-03-31
Owner6 | Owner3 | HEL | EFG System | ISS_012584 | Data definitions | 2018-09-30 | 2025-12-31 |  | In progress | N/A | 2025-12-31 | DEC | 2025 | 2019-03-31
Owner6 | Owner3 | IFR | FGH System | ISS_012585 | Data definitions | 2019-05-23 | 2020-12-31 | Type 1 - Critical | In progress | N/A | 2020-12-31 | DEC | 2020 | 2019-03-31
Owner6 | Owner1 | IFR | FGH System | ISS_012586 | Data definitions | 2019-03-29 | 2019-12-31 |  | In progress | CCAR | 2019-12-31 | DEC | 2019 | 2019-03-31
Owner6 | Owner3 | RBC | FGH System | ISS_012588 | Data definitions | 2019-05-23 | 2019-03-31 |  | In progress | CCAR | 2019-03-31 | MAR | 2019 | 2019-03-31

## Sheet1
Management_Owner | varchar | not null
Issue_Owner | varchar | not null
Source_of_Issue | varchar | not null
Source_System | varchar | not null
Issue_ID | varchar | not null
Issue_Subject | varchar | not null | max
OECD | date | not null
RECD | date | nullable
Level | varchar | nullable
Notes(Status Update) | varchar | not null
CCAR_v.non-CCAR | varchar | nullable
Completion Date | date | not null
MM | varchar | not null
YYYY | varchar | not null
Category | varchar | not null
asofdate | date | not null